## Plans
Is done | № | Description | Estimated time (hour) | Real time (hour) | TODO |  |  |  | Hours
+ | 1 | Создать новый солюшин | 0.4 | 0.4 | Установщик |  | 0 | Estimated time | 108.4
+ | 2 | Спроектировать архитектуру | 1 | 1 | Family | BD | 0 | Real time | 70.4
+ | 3 | Спроектировать базу данных | 1 | 2 |  |  | 0 | Remaining time | 59
+ | 4 | Создать базу данных | 2 | 8 |  |  | 0
+ | 5 | Создать сервисы для работы с базой данных | 8 | 12 | Сайт для скачивания установщика |  | 0
| 6 | DailyReports (CalendarDataBuilder) | 4 | 8 | Check for updates |  | 4
| 7 | Unit-tests DailyReports | 4 |  | Шаблон чека | BD | 4
+ | 8 | ReportGenetator | 8 | 8 | Возможность backup data |  | 0
+ | 9 | Unit-tests ReportGenerator | 4 | 4 | Данные по умолчанию (рус валюты) |  | 0
+ | 10 | Summaries | 2 | 2 | Read me или about |  | 0
+ | 11 | Unit-tests Summaries | 2 | 2 | Страница в Wiki |  | 0
| 12 | LimitGenerator | 16 |  | Платный контент |  | 16
| 13 | Unit-tests LimitGenerator | 8 |  | Хочу…генерация решений (советы) | Logic | 8
| 14 | ForecastsGenerator | 16 |  |  |  | 16
| 15 | Unit-tests ForecastsGenerator | 8 |  |  |  | 8
+ | 16 | Unit-tests for services | 5 | 5 | Синхронизация с карточкой | Logic | 0
+ | 17 | User actions history implement | 6 | 8 |  |  | 0
+ | 18 | Defaults loader | 5 | 5 |  |  | 0
| 19 | UI: on remove category ask remove limits | 1 |  |  |  | 1
+ | 20 | Unit-tests base | 2 | 1 |  |  | 0
+ | 21 | RecordService - tests on get methods | 3 | 4 |  |  | 0
| 22 | ReportBuilderSettings - currency | 2 |  | Force execute event | UI | 2
| 23 | IEventService - tests |  |  |  |  | 0
| 24 | DataGrid - select columns |  |  |  |  | 0
| 25 | Font size |  |  | Clear history | Logic | 0
| 26 | ScheduleService - tests |  |  | Update category list | Logic | 0
| 27 | StorageSummary - tests |  |  | Поиск по категориям | UI | 0
| 28 | Font family |  |  | Обновление курсов валют |  | 0
| 29 | Defaults: use services for write history |  |  | Replace defaults to database |  | 0
| 30 |  |  |  | Цели (targets) -> когда смогу | BD | 0
| 31 |  |  |  | Если приложение падает, отправлять мейл. Хранить ошибки в бд |  | 0
| 32 | [5 empty] | 0
| 33 | [5 empty] | 0
| 34 | [5 empty] | 0
| 35 | [5 empty] | 0
| 36 | Autofac |  |  |  |  | 0
| 37 | [5 empty] | 0
| 38 | [5 empty] | 0
| 39 | [5 empty] | 0
| 40 | [5 empty] | 0
| 41 | [5 empty] | 0
| 42 | [5 empty] | 0
| 43 | [5 empty] | 0
| 44 | [5 empty] | 0
| 45 | [5 empty] | 0
| 46 | [5 empty] | 0
| 47 | [5 empty] | 0
| 48 | [5 empty] | 0
| 49 | [5 empty] | 0
| 50 | [5 empty] | 0
| 51 | [5 empty] | 0

## Estimate
Description | Time (days) | Today | Deadline | Remain (days) | Estimated time | Remained time
|  | 2018-03-19 | 2018-07-01 | 104 | 131 | -27
SimpleEventDetailsView | 0
MoneyTransferEventDetailsView | 0
RepayDebtEventDetailsView | 0
PlanningPage -> Limits list + LimitDetailsView | 0
Refactoring: custom controls (category selection dialog, comission control, currency exchange rate selector) | 0
Refactoring: page options and reload requirements | 0
Refactoring: base details view | 0
Refactoring: models & view models | 2
Refactoring: services (onAdd, onEdit, onDelete methods) | 0
Refactoring: Commission in entities(models) to separate entity | 1
Refactoring: default command implementations | 0
Refactoring: Check details view on enums | 0
Refactoring: List view -> enum value converter (instead of combobox) | 0
Refactoring: see all details views on margin, result value, perfect visual style | 0
Refactoring: Придумать заполнение Combobox nullable ids | 1
Transactions page. Records list | 0
Transactions page. Record details | 0
Transactions page. Filter | 3
Transactions page. Save filter to DB | 0
Transactions page. Show for period | 0
Transactions page. Show planned events | 0
Transactions page. Show money transfers in list | 0
Transactions page. Context menu for planned | 1
Transactions page. Add cheque | 0
Refactoring: create separate control for period selector | 1
Refactoring: create separate control for data filter | 1
CalendarDataBuilder. Day data | 7
CalendarDataBuilder. Limits | 7
Calendar page. Base view | 3
Calendar page. Show for period | 3
Calendar page. Calendar day control | 2
Calendar page. Filter | 2
Calendar page. Save filter to DB | 1
Calendar page. Open list/details on double click | 4
LimitGenerator | 21
ForecastsGenerator | 21
Reports page. Base view | 2
Reports page. Pie chart | 7
Reports page. Table | 1
Reports page. Bar chart | 4
Reports page. Filter | 3
Reports page. Show for period | 1
Reports page. Data builder | 2
Dashboard. Base view | 2
Dashboard. Events for confirmation DB | 3
Dashboard. Events for confirmation View | 1
Dashboard. Events to be executed today DB | 2
Dashboard. Events to be executed today View | 1
Dashboard. Today transactions | 1
Dashboard. Balance summary | 1
Dashboard. Alerts: exceeded limit, debt should be repayed… | 3
Settings page: general data | 1
Settings page: theme and language | 2
validation erros (Details view) | 2
Обработчики delete exceptions | 1
Currency dublicates | 0
Expander size: fix columns size | 0
Quick access (Ctrl + N, Delete etc) | 1
Storages page -> double click -> edit | 1
Storages page -> drug/drop | 1
For every new entity fill default required foreign key values | 1
Header окна + название выбранной страницы | 1
Categories page -> expand all/collapse all | 1
Ограничения на строки (DetailsView) | 1
Storage page -> summary for every group | 1
Events: "apply now" menu item | 1
Events: "Create transaction" menu item -> show record details | 1

## Bugs
Bugs | Refactoring | Features (UI) | Features (Global)
|  | Ограничения на строки (DetailsView) | User settings - autofill description from selected category
| Commission in entities(models) to separate entity | validation erros (Details view) | User local settings -> main menu shown
|  | All buttons ToggleButton -> change icon when unckecked and change tooltip | Storage page -> summary for every group
| Придумать заполнение Combobox nullable ids |  | Add family
| Debt penalty view model. Replace command |  | Advice generator ?
Debts list -> foreground green/red | Debts page. Model. Binding. | Categories page -> expand all/collapse all | Installer
Money transfer events list -> foreground red if commission exists | Replace all additional fields from models to view models | Storage group -> серый цвет | Add targets
| Check details view on enums | Header окна + название выбранной страницы
List view -> enum value converter (instead of combobox)
Пересмотреть все модели. Прорефакторить
Обработчики delete exceptions
Quick access (Ctrl + N, Delete etc)
Storages page -> double click -> edit
Storages page -> drug/drop
For every new entity fill default requires foreign key values
Сделать красивое окошко Limit details

## Refactoring
Requires refactoring | Details
Expander | Style
Expander | Стиль для перевернутого header
Planning page | Event grids -> one style for grid/border
Planning page | One context menu for events
Tool bar menu | Style for buttons
Tool bar menu | Create Add/Edit/Delete buttons
DataGrid | Style
All pages | Use EntityListViewModel for all pages (if necessary)
Style | Вынести все цвета в отдельный файл (Greed, Red)
Style | Вынести opacity в отдельный файл стилей
All pages | Replace OrderBy into the service
Style | Создать свои стили для всех компонентов (не использовать MetroStyle/MaterialDesign)