## Plans
Is done | № | Description | Estimated time (hour) | Real time (hour) | TODO |  |  |  | Hours
+ | 1 | Создать новый солюшин | 0.4 | 0.4 | Установщик |  | 0 | Estimated time | 108.4
+ | 2 | Спроектировать архитектуру | 1 | 1 | Family | BD | 0 | Real time | 70.4
+ | 3 | Спроектировать базу данных | 1 | 2 |  |  | 0 | Remaining time | 59
+ | 4 | Создать базу данных | 2 | 8 |  |  | 0
+ | 5 | Создать сервисы для работы с базой данных | 8 | 12 | Сайт для скачивания установщика |  | 0
| 6 | DailyReports (CalendarDataBuilder) | 4 | 8 | Check for updates |  | 4
| 7 | Unit-tests DailyReports | 4 |  | Шаблон чека | BD | 4
+ | 8 | ReportGenetator | 8 | 8 | Возможность backup data |  | 0
+ | 9 | Unit-tests ReportGenerator | 4 | 4 | Данные по умолчанию (рус валюты) |  | 0
+ | 10 | Summaries | 2 | 2 | Read me или about |  | 0
+ | 11 | Unit-tests Summaries | 2 | 2 | Страница в Wiki |  | 0
| 12 | LimitGenerator | 16 |  | Платный контент |  | 16
| 13 | Unit-tests LimitGenerator | 8 |  | Хочу…генерация решений (советы) | Logic | 8
| 14 | ForecastsGenerator | 16 |  |  |  | 16
| 15 | Unit-tests ForecastsGenerator | 8 |  |  |  | 8
+ | 16 | Unit-tests for services | 5 | 5 | Синхронизация с карточкой | Logic | 0
+ | 17 | User actions history implement | 6 | 8 |  |  | 0
+ | 18 | Defaults loader | 5 | 5 |  |  | 0
| 19 | UI: on remove category ask remove limits | 1 |  |  |  | 1
+ | 20 | Unit-tests base | 2 | 1 |  |  | 0
+ | 21 | RecordService - tests on get methods | 3 | 4 |  |  | 0
| 22 | ReportBuilderSettings - currency | 2 |  | Force execute event | UI | 2
| 23 | IEventService - tests |  |  |  |  | 0
| 24 | DataGrid - select columns |  |  |  |  | 0
| 25 | Font size |  |  | Clear history | Logic | 0
| 26 | ScheduleService - tests |  |  | Update category list | Logic | 0
| 27 | StorageSummary - tests |  |  | Поиск по категориям | UI | 0
| 28 | Font family |  |  | Обновление курсов валют |  | 0
| 29 | Defaults: use services for write history |  |  | Replace defaults to database |  | 0
| 30 |  |  |  | Цели (targets) -> когда смогу | BD | 0
| 31 |  |  |  | Если приложение падает, отправлять мейл. Хранить ошибки в бд |  | 0
| 32 | [5 empty] | 0
| 33 | [5 empty] | 0
| 34 | [5 empty] | 0
| 35 | [5 empty] | 0
| 36 | Autofac |  |  |  |  | 0
| 37 | [5 empty] | 0
| 38 | [5 empty] | 0
| 39 | [5 empty] | 0
| 40 | [5 empty] | 0
| 41 | [5 empty] | 0
| 42 | [5 empty] | 0
| 43 | [5 empty] | 0
| 44 | [5 empty] | 0
| 45 | [5 empty] | 0
| 46 | [5 empty] | 0
| 47 | [5 empty] | 0
| 48 | [5 empty] | 0
| 49 | [5 empty] | 0
| 50 | [5 empty] | 0
| 51 | [5 empty] | 0

## Estimate
Type | Destination | Description | Time (days) | Today | Deadline | Remain (days) | Estimated time | Remained time
|  |  |  | 2018-04-26 | 2018-07-01 | 66 | 124 | -58
| Calendar page | Base view | 0
| Calendar page | Show for period | 0
| Calendar page | Calendar day control | 0
| Calendar page | Settings | 0
| Calendar page | Save settings to DB | 0
| CalendarDataBuilder | Day data | 0
| Categories page | Expand all/collapse all | 0
| Debts list | Foreground green/red | 0
Feature | Details view | SimpleEventDetailsView | 0
Feature | Details view | MoneyTransferEventDetailsView | 0
Feature | Details view | RepayDebtEventDetailsView | 0
| Money transfer events list | Foreground red if commission exists | 0
Feature | PlanningPage | Limits list + LimitDetailsView | 0
Bug | Record details | When change income/expence resultat amount isn't changed | 0
Bug | Record details | Description change doesn't make form dirty | 0
Bug | Record details | Make storage as required field | 0
| Storages page | double click -> edit | 0
| Transactions page | Records list | 0
| Transactions page | Record details | 0
| Transactions page | Filter | 0
| Transactions page | Save filter to DB | 0
| Transactions page | Show for period | 0
| Transactions page | Show planned events | 0
| Transactions page | Show money transfers in list | 0
| Transactions page | Context menu for planned | 0
| Transactions page | Add cheque | 0
Refactoring |  | Custom controls (category selection dialog, comission control, currency exchange rate selector) | 0
Refactoring |  | Page options and reload requirements | 0
Refactoring |  | Base details view | 0
Refactoring |  | Services (onAdd, onEdit, onDelete methods) | 0
Refactoring |  | Default command implementations | 0
Refactoring |  | Check details view on enums | 0
Refactoring |  | List view -> enum value converter (instead of combobox) | 0
Refactoring |  | See all details views on margin, result value, perfect visual style | 0
Refactoring |  | Create separate control for period selector | 0
Refactoring |  | Create separate control for data filter | 0
Bug |  | Currency dublicates | 0
Bug |  | Expander size: fix columns size | 0
|  | For every new entity fill default required foreign key values | 0
Bug | Calendar day control | Show dots when many transactions | 1
| Calendar page | Cell height in settings | 1
Feature | Categories page | Add child | 0
Feature | Category selector + filter | Show inactive + tool bar for expand/collapse all | 1
Refactoring | Category view model | Remove IsExpandedMainView/IsSelectedMainView | 1
| Dashboard | Events for confirmation View | 1
| Dashboard | Events to be executed today View | 1
| Dashboard | Today transactions | 1
| Dashboard | Balance summary | 1
Bug | Data filter control | Scroll doen't work on tree view | 1
Bug | Data filter control | not all categories selected but shows (All). And filter is applied strange | 1
| Details view | Ограничения на строки | 1
| Events | "apply now" menu item | 1
| Events | "Create transaction" menu item -> show record details | 1
| Reports page | Table | 1
| Reports page | Show for period | 1
Refactoring | Services | Cleanup | 1
| Settings page | General data | 1
| Storages page | drug/drop | 1
| Storages page | Summary for every group | 1
Feature | Storages page | Money transfers list -> add filters | 1
Feature | Storages page | Drug&drop storage group order. Store order in database | 1
| Transactions Page | Show/hide planned transactions | 1
| Transactions page | Separate transaction list by day (add line between different day transactions) | 1
Perfomance | Transactions page | Applying filter on categories takes a lot of time | 1
Bug | Transactions service | Take existing currency exchange rate | 1
Refactoring |  | Commission in entities(models) to separate entity | 1
Refactoring |  | Придумать заполнение Combobox nullable ids | 1
Bug |  | Обработчики delete exceptions | 1
Feature |  | Quick access (Ctrl + N, Delete etc) | 1
Feature |  | Header окна + название выбранной страницы | 1
|  | Update limits on record/money transfer is added | 1
|  | Event execution | 1
Bug |  | Negative value in case when $-100 | 1
| Calendar page | Apply filter | 2
| Dashboard | Base view | 2
| Dashboard | Events to be executed today DB | 2
Feature | Data filter control | Category tree context menu (expand all, collapse all, select all, upselect all, select branch, unselect branch) | 0
| Reports page | Base view | 2
| Reports page | Data builder | 2
| Settings page | Theme and language | 2
Refactoring |  | Models & view models | 2
Bug |  | validation erros (Details view) | 2
| Dashboard | Events for confirmation DB | 3
| Dashboard | Alerts: exceeded limit, debt should be repayed… | 3
| Reports page | Filter | 3
| Calendar page | Open list/details on double click | 4
| Reports page | Bar chart | 4
| CalendarDataBuilder | Limits | 7
| Reports page | Pie chart | 7
|  | LimitGenerator | 21
|  | ForecastsGenerator | 21
Bug | Data filter control | Save IsCategoryBranchSelection to database | 1
Feature | Transactions page | Add record/money transfer to separate buttons | 1

## Bugs
Bugs | Refactoring | Features (UI) | Features (Global)
User settings - autofill description from selected category
User local settings -> main menu shown
|  | All buttons ToggleButton -> change icon when unckecked and change tooltip | Storage page -> summary for every group
Add family
| Debt penalty view model. Replace command |  | Advice generator ?
| Debts page. Model. Binding. |  | Installer
| Replace all additional fields from models to view models | Storage group -> серый цвет | Add targets
Header окна + название выбранной страницы
List view -> enum value converter (instead of combobox)
Пересмотреть все модели. Прорефакторить

## Refactoring
Requires refactoring | Details
Expander | Style
Expander | Стиль для перевернутого header
Planning page | Event grids -> one style for grid/border
Planning page | One context menu for events
Tool bar menu | Style for buttons
Tool bar menu | Create Add/Edit/Delete buttons
DataGrid | Style
All pages | Use EntityListViewModel for all pages (if necessary)
Style | Вынести все цвета в отдельный файл (Greed, Red)
Style | Вынести opacity в отдельный файл стилей
All pages | Replace OrderBy into the service in the entity selections
Style | Создать свои стили для всех компонентов (не использовать MetroStyle/MaterialDesign)
Perfomance | Replace all data loading in pages into the loaded event instead of constructor

## Help
Type
Bug
Feature
Feature(G)
Refactoring
Perfomance